## gnattchart
Visit: http://abcaus.in | [6 empty] | Download Help File
| Project Title: |  | Audit |  |  |  |  | Gnatt Chart
| Sl No | Name of the Activity |  | Start Date | End Date | Audit Gnatt Chart
| 1 | Audit Planning
| 2 | Preliminery Discussion |  | 2012-11-06 | 2012-11-09 | ¦¦¦¦
| 3 | Preliminery Survey |  | 2012-11-12 | 2012-11-12 | ¦
| 4 | Planning Memorandum |  | 2012-11-12 | 2012-11-17 | ¦¦¦¦¦¦
Field Work
| 5 | Analysis and Evaluation |  | 2012-11-18 | 2012-11-21 | ¦¦¦¦
| 6 | Performing Test and Procedures |  | 2012-11-22 | 2012-12-03 | ¦¦¦¦¦¦¦¦¦¦¦¦
Exit Discussions
| 7 | Rough Draft |  | 2012-12-04 | 2012-12-06 | ¦¦¦
| 8 | Discussion Draft |  | 2012-12-07 | 2012-12-09 | ¦¦¦
| 9 | Final Report |  | 2012-12-10 | 2012-12-13 | ¦¦¦¦
| 10 | Audit Followup |  | 2012-12-15 | 2012-12-22 | ¦¦¦¦¦¦¦¦
Note on D4: Fill Here
ABCAUS GANTT CHART
Help
EXIT
Print Chart