## Six Sigma Project Charter
Lean6™ |  | Six Sigma Project Charter |  |  |  |  | Leanmap.com
Six Sigma for Excel | [6 empty] | Navigating to Results
1 | Process |  |  | Manufacturing process of custom-made doors
Process selected for improvement:
2 | Description |  |  | Increase sales by improving speed and quality
Purpose and goals of the project:
3 | Objective |  | Parameter | Measure |  | Baseline (now) |  | Goal (future) |  | Unit of Measure
Key metrics of the project:
|  |  | Lead time | Time from order-entry to shipment |  | 6 |  | 3 |  | days
|  |  | Reject rate | Percentage of units rejected by customer |  | 0.1 |  | 0.01 |  | % shipped
|  |  | Scrap Rate | Percentage of units failed and scrapped |  | 10 |  | 2 |  | % produced
4 | Return/Value |  | Parameter | Impact of Improvement | [5 empty] | Return
Expected financial impact:
|  |  | Lead time | 50% shorter lead-time = 15% more orders | [5 empty] | $150k
|  |  | Reject rate | 10x reduced rejects = retaining more customers = 20% higher order volume | [5 empty] | $200k
|  |  | Scrap Rate | 5x reduced scrap rate = product-cost reduced from $550k to $510k | [5 empty] | $40k
5 | Team |  | Names | Function | Responsibility
Names and responsibilities:
|  |  | J. Jones | Quality Manager | Analyze rejects over past 12 months and list top 5 reasons
|  |  | M. Nickolsen | Sales Manager | Define value of lost orders due to rejects
|  |  | Y. Chu | Controller | Consolidate value of customer rejects
|  |  | P. Rickfield | Production Manager | Account scrap by (1) assembly (2) material (3) test (4) visual.
|  |  | H. Finkler | Process Engineer | Update drawings/procedures to minimize assembly errors.
|  |  | A. Betz | Project Manager | Run Kaizen Blitz to improve process performance
6 | Scope |  |  | Project includes manufacturing process. Skills of people and capability of the support-system are excluded.
Project scope, what is included, what is excluded:
7 | Customer benefit |  |  | Faster delivery and lower defect rate, lower total cost, higher satisfaction.
Improvement that the customer will notice:
8 | Schedule |  | Phase | Deliverables | Responsible |  |  |  | Date
Item and completion dates:
|  |  | Define | Project Charter | J. Jones |  |  |  | 2020-01-01
|  |  | Measure | Baseline Capability | Y. Chu |  |  |  | 2020-02-02
|  |  | Analyze | Analysis + Action Plan | Jones, Finkler, Chu, Nickolsen |  |  |  | 2020-03-03
|  |  | Improve | Improvements | P. Rickfield |  |  |  | 2020-04-04
|  |  | Control | Control Plan | H. Finkler |  |  |  | 2020-05-05
5 | Support |  | Set priorities to allow team-members to invest 2x 4 hours per member per week on this project = 48 man-hours per week work-load
Requirements to execute plan
Note on R6: Description - State one goal only - Describe goal precisely
Note on K46: Define Project Charter: - Schedule - Deliverables - Responsibilities
Note on K48: Measure - Map the Process - Baseline Capabilities
Note on K50: Analyze - Organize data - Cause & Effect - Control Charts - Summarize findings - Create Action Plan
Note on K52: Improve - Eliminate failures (FMEA) - Optimize processes (DOE)
Note on K54: Control - Control Plan - Control Charts