Microsoft® Operations Framework

Version 4.0

Envision Service Management Function

FPO

Published: April 2008

For the latest information, please see
microsoft.com/technet/SolutionAccelerators

Copyright © 2008 Microsoft Corporation. This documentation is licensed to you under the Creative Commons Attribution License.  To view a copy of this license, visit http://creativecommons.org/licenses/by/3.0/us/ or send a letter to Creative Commons, 543 Howard Street, 5th Floor, San Francisco, California, 94105, USA.  When using this documentation, provide the following attribution: The Microsoft Operations Framework 4.0 is provided with permission from Microsoft Corporation.

This documentation is provided to you for informational purposes only, and is provided to you entirely "AS IS". Your use of the documentation cannot be understood as substituting for customized service and information that might be developed by Microsoft Corporation for a particular user based upon that user’s particular environment. To the extent permitted by law, MICROSOFT MAKES NO WARRANTY OF ANY KIND, DISCLAIMS ALL EXPRESS, IMPLIED AND STATUTORY WARRANTIES, AND ASSUMES NO LIABILITY TO YOU FOR ANY DAMAGES OF ANY TYPE IN CONNECTION WITH THESE MATERIALS OR ANY INTELLECTUAL PROPERTY IN THEM.

Microsoft may have patents, patent applications, trademarks, or other intellectual property rights covering subject matter within this documentation. Except as provided in a separate agreement from Microsoft, your use of this document does not give you any license to these patents, trademarks or other intellectual property.

Information in this document, including URL and other Internet Web site references, is subject to change without notice. Unless otherwise noted, the example companies, organizations, products, domain names, e-mail addresses, logos, people, places and events depicted herein are fictitious.

Microsoft is a registered trademark of Microsoft Corporation in the United States and/or other countries.

The names of actual companies and products mentioned herein may be the trademarks of their respective owners.

You have no obligation to give Microsoft any suggestions, comments or other feedback ("Feedback") relating to the documentation. However, if you do provide any Feedback to Microsoft then you provide to Microsoft, without charge, the right to use, share and commercialize your Feedback in any way and for any purpose. You also give to third parties, without charge, any patent rights needed for their products, technologies and services to use or interface with any specific parts of a Microsoft software or service that includes the Feedback. You will not give Feedback that is subject to a license that requires Microsoft to license its software or documentation to third parties because we include your Feedback in them.

Contents

Position of the Envision SMF Within the MOF IT Service Lifecycle	1

Why Use the Envision SMF?	1

Envision Service Management Function Overview	2

Envision SMF Role Types	2

Goals of Envisioning	4

Key Terms	5

Envision Process Flow	6

Process 1: Organize the Core Team	8

Activities: Organize the Core Team	8

Process 2: Write the Vision/Scope Document	10

Activities: Write the Vision/Scope Document	10

Process 3: Approve the Vision/Scope Document	12

Activities: Approve the Vision/Scope Document	12

Conclusion	13

Feedback	13

# Position of the Envision SMF Within the MOF IT Service Lifecycle

The MOF IT service lifecycle encompasses all of the activities and processes involved in managing an IT service: its conception, development, operation, maintenance, and—ultimately—its retirement. MOF organizes these activities and processes into Service Management Functions (SMFs), which are grouped together in lifecycle phases. Each SMF is anchored within a lifecycle phase and contains a unique set of goals and outcomes supporting the objectives of that phase. The SMFs can be used as stand-alone sets of processes, but it is when SMFs are used together that they are most effective in ensuring service delivery at the desired quality and risk levels.

The Envision SMF belongs to the Deliver Phase of the MOF IT service lifecycle. The following figure shows the place of the Envision SMF within the Deliver Phase, as well as the location of the Deliver Phase within the IT service lifecycle.

Figure 1. Position of the Envision SMF within the IT service lifecycle

Before you use this SMF, you may want to read the following MOF 4.0 guidance to learn more about the MOF IT service lifecycle and the Deliver Phase:

- MOF Overview

- Deliver Phase Overview

# Why Use the Envision SMF?

This SMF should be useful to anyone who is tasked with forming a core project team, preparing and delivering a vision/scope document that clearly communicates the project’s vision and the scope of that vision, and preparing a risk assessment.

It addresses how to do the following:

- Organize the core project team.

- Write the vision/scope document.

- Approve the vision/scope document.

# Envision Service Management Function Overview

Envisioning is the first step a project team takes to turn business requirements into a change in the IT infrastructure or into new IT services that can be delivered into production. It’s the process of unifying a team with a common vision and is a key requirement for ensuring a project’s success. A project team must have a clear vision of what it wants to accomplish and be able to communicate this vision in terms that motivate team members, their customers, and their stakeholders. The process of envisioning begins in the Plan Phase and concludes in the Deliver Phase.

During envisioning, project teams identify and analyze business needs and requirements so that they can begin planning a solution. That solution might be a single application, a full IT service, or an addition to or modification of existing IT infrastructure. The primary team role type driving envisioning is Product Management, whose main goal is to ensure that the customer’s identified business needs are addressed. More information about the Product Management role type, and other role types involved in the Envision SMF, can be found in the Envision SMF Role Types table that follows.

By creating high-level views of the project’s goals and constraints, envisioning serves as an early form of planning. It sets the stage for the more formal planning process that will take place during the project’s planning phase.

The guidance provided by the Envision SMF is designed to help:

- Management choose the core project team and create the project structure document that specifies the roles and responsibilities of the team members.

- The project team create the vision/scope document, perform a risk assessment, and complete the milestone review report.

- The team members, customers, and stakeholders approve the milestone review report for the Vision/Scope Approved Milestone. At this milestone, the team, customers, and stakeholders agree on the overall direction of the project: the scope of features the project includes, the general timetable for delivering the project’s solution, and the risks associated with the project. After the Vision/Scope Approved Milestone, project teams continue to the planning phase.

## Envision SMF Role Types

The primary team accountability that applies to the Envision SMF is the Solution Accountability. The role types within that accountability and their primary activities within this SMF are displayed in the following table.

Table 1. Project Accountability and Its Attendant Role Types

| Role Type | Responsibilities | Role in This SMF |
| --- | --- | --- |
| Solution Manager | - Accountable role - Owns all SMFs in this accountability - Acts as project director for all projects - Resolves conflicts between projects | - Ongoing oversight |
| Program Manager | - Drives design, schedule, and resources at the project level | - Sets design goals - Describes the solution concept - Creates the project structure |
| Developer | - Builds the agreed-to solution | - Builds prototypes - Investigates development and technology options - Analyzes the project’s feasibility |
| Tester | - Tests to accurately determine the status of solution development | - Tests strategies - Tests acceptance criteria - Documents project implications |
| Product Manager | - Acts as the customer advocate - Helps drive shared project vision - Manages customer expectations | - Sets overall goals - Identifies customer needs - Determines project requirements - Produces the vision/scope document |
| User Experience | - Acts as the user advocate on project teams - Helps define user requirements - Helps design to meet user requirements | - Documents user performance requirements - Documents project test implications |
| Release Management | - Evaluates the solution design - Documents operations requirements to ensure they’re met by the design - Creates a pilot, deployment plan, and schedule - Manages site deployment | - Documents deployment implications - Documents operations management and supportability - Documents operations acceptance criteria |
| Operations Experience | - Advocates for operations on the project team - Brings in operations experts as needed for detailed information - Coordinates with release management | - Documents operations performance requirements |
| Test Manager | - Owns all testing across all project teams - Develops testing strategy and plans - Ensures that best practice test methods are used | - Ongoing oversight |

## Goals of Envisioning

The primary goals of envisioning are to form the core project team, prepare and deliver a vision/scope document that clearly communicates the project’s vision and the scope of that vision, and prepare a risk assessment. Table 2 shows the desired outcomes of the Envision SMF goals and lists measures that you can use to gauge how successfully you have achieved these goals after completing this SMF.

Table 2. Outcomes and Measures of the Envision SMF Goals

| Outcomes | Measures |
| --- | --- |
| The vision and scope of the project are clearly documented and understood by the team and the customer. | - No miscommunications and misunderstandings are found later on in the project. - The vision and scope remain largely intact throughout the project. - The vision/scope document is approved by the team and stakeholders. - Signoff on the Vision/Scope Approved Milestone occurs. |
| The project’s risks are clearly documented and understood by the team and the customer. | - No unaddressed issues occur during the project. - Risk assessment is approved by the team and stakeholders. - Signoff on the Vision/Scope Approved Milestone occurs. |

## Key Terms

The following table contains definitions of key terms found in this guide.

Table 3. Key Terms

| Term | Definition |
| --- | --- |
| Customer | The customer is the person or organization that commissions and funds the project. |
| Interim milestone | Early progress indicators that segment large work efforts into manageable portions. The Deliver Phase suggests a set of interim milestones, but project teams should define their own interim milestones that make sense for their projects. |
| Milestone | A project synchronization point. Major milestones mark the transition of a project from one phase to the next phase. They also transfer primary responsibility from one role to another role. The Deliver Phase service management functions (SMFs) correspond to major Microsoft Solutions Framework (MSF) milestones. |
| Scope | A view of the project’s vision limited by constraints such as time and resources. Solution scope describes the solution’s features and deliverables. Project scope describes the work to be performed by the team. |
| Solution | A coordinated delivery of technologies, documentation, training, and support that successfully responds to a customer’s business problem. Solutions typically combine people, processes, and technology to solve problems. |
| Stakeholder | Stakeholders are individuals or groups who have an interest in the outcome of the project—although their goals and priorities are not always identical to the customer’s. Examples of stakeholders include departmental managers who will be affected by the solution, IT staff members who are responsible for running and supporting the solution, and functional managers who contribute resources to the project team. |
| Users | The people who interact with the solution to perform their jobs. |
| Vision | Describes the fundamental goals of the solution. |

# Envision Process Flow

Figure 2 illustrates the process flow for envision management. This flow consists of the following processes:

- Organize the core project team.

- Write the vision/scope document.

- Approve the vision/scope document.

Figure 2. Envision process flow

Figure 3 shows the process flow in more detail.

Figure 3. Envision process flow—detailed

# Process 1: Organize the Core Team

The first process in envisioning is for management to organize the core project team and produce the project structure document.

Figure 4. Organize the core team

## Activities: Organize the Core Team

During this process, management assigns core members to the project team. Typically, management does not assemble the full team yet. The initial team often plays multiple roles until all members are in place.

After assigning the core team, management creates a project structure document that describes the team’s organization and the roles and specific responsibilities assigned to each team member. The project structure document also clarifies the chain of accountability to the customer and specifies the designated points of contact that the project team has with the customer. These can vary depending on the circumstances of the project.

Table 4. Activities and Considerations for Organizing the Core Team

| Activities | Considerations |
| --- | --- |
| Assign core members to the project team | Key questions: - What is the project’s scale—small, medium, or large? - Will members be dedicated to the team or will they work on other projects as well? - Will members have multiple roles or will each member have a unique role? - Does the organization have an existing team model for IT projects? - Are team members experienced in their assigned roles? Is training required? Inputs: - Project proposal Outputs: - Project structure document, which includes: - Project goals, objectives, assumptions, and constraints. - Project scope. - Roles and responsibilities. - Project protocols. - Risk and issue assessment. - Project glossary. - Core members assigned to the project team Best practices: - Although team members can fulfill multiple roles in most cases, the team members who are assigned Development and Test roles should not take on other roles. - Team members in the Product Management and Program Management roles should be fully dedicated to the project during envisioning. - In the project structure document, describe milestones early on so the customer understands when things are supposed to occur and that project the team can use during its planning activities. This document also identifies the checkpoints where milestone reviews to assess the project’s quality and its results will occur. - Document the project’s organizational structure, ensuring that all team members understand their roles in making the project a success, clarifying lines of reporting and decision making, and providing key stakeholders the opportunity to ensure that the project’s organizational structure (the project’s form) will facilitate the work (the project’s function). |

# Process 2: Write the Vision/Scope Document

In this process, the project team writes the vision/scope document and performs a risk assessment.

Figure 5. Write the vision/scope document

## Activities: Write the Vision/Scope Document

During this process, the project team completes the first draft of the vision/scope document and distributes it to the team, customers, and stakeholders for review. During the review process, the document undergoes multiple iterations of feedback, discussion, and change.

The vision/scope document is usually written at a strategic level of detail and the project team uses it during planning as the context for developing technical specifications and project management plans in greater detail. It provides clear direction for the project team; outlines explicit project goals, priorities, and constraints; and sets customer expectations.

Project vision and project scope are distinct concepts, and successful projects require both. Project vision is an unlimited view of the solution. Project scope identifies the parts of the vision that a project team can accomplish within its constraints. The vision/scope document defines both concepts.

Another key activity of this process is for the team to assess and document the project risks. This is done using the Risk Template.

The following table lists the activities involved in this process. These activities include:

- Writing the vision/scope document.

- Assessing and documenting project risks.

Table 5. Activities and Considerations for Writing the Vision/Scope Document

| Activities | Considerations |
| --- | --- |
| Write the vision/scope document | Key questions: - Does the customer have a clear vision for the project? - What are the business goals that the project is trying to accomplish? - What constraints (time or resources) must be placed on the vision? - Does the project team understand the profiles of the solution’s users? - Does the organization have documentation standards for similar projects? - Does the organization have a change control process? For information about change control, see the Change and Configuration SMF. Inputs: - Project structure document - Reliability requirements (See Reliability SMF) - Policy requirements (See Reliability SMF) Outputs: - Vision/scope document, which includes: - Business opportunity - Solutions concept - Scope - Solution design strategies |
| Assess and document project risks | Key questions: - Can the project team identify any known risks to the project? - How can the probability of each risk be estimated? - Can the team estimate the impact of each risk if it manifests? Input: - None Output: - Risk assessment using the Risk Template Best practices: - Plan and anticipate risks to avoid surprises that have a negative impact. - If the team uses a numeric scale to assess the probability and impact of a risk, it can compare the severity of each risk by multiplying the two numbers. For more information about risk management, see the Governance, Risk, and Compliance SMF. |

# Process 3: Approve the Vision/Scope Document

Finally, the project team obtains signoff from the customer and the stakeholders and then completes the milestone review report.

Figure 6. Approve the vision/scope document

## Activities: Approve the Vision/Scope Document

During this process, the team completes the milestone review report for the Vision/Scope Approved Milestone. The team, customers, and stakeholders sign off on this report to indicate their approval of the vision/scope document. Signoff also indicates that the team, customers, and stakeholders agree that the project team has met the requirements for completing the Vision/Scope Approved Milestone and that the project is ready to proceed to planning.

Table 6. Activities and Considerations for Approving the Vision/Scope Document

| Activities | Considerations |
| --- | --- |
| Sign off on the milestone review report for the Vision/Scope Approved Milestone | Key questions: - Do the team, customers, and stakeholders agree on the vision? - Do the team, customers, and stakeholders agree on the scope of the project? - Has the project team met the requirements of the Vision/Scope Approved Milestone? Inputs: - Vision/scope document - Risk assessment (Risk Template) Output: - Milestone review report document - Best Practices: - Conduct a close-out meeting to present the vision/scope document in order to: - Ensure the right understanding of the problem/opportunity. - Ensure the customer (or service recipient) has a clear picture and a preview of the solution. - Confirm the scope. - Communicate any highlights (risks and issues). |

# Conclusion

The Envision SMF describes the process for forming a core project team, preparing and delivering a vision/scope document that clearly communicates the project’s vision and the scope of that vision, and preparing a risk assessment.

The major Envision processes described by the SMF are:

- Organize the core project team.

- Write the vision/scope document.

- Approve the vision/scope document.

## Feedback

Please direct questions and comments about this guide to mof@microsoft.com.